AMREF INTERNATIONAL UNIVERSITY

SCHOOL OF PUBLIC HEALTH

DEPARTMENT OF HEALTH SYSTEMS MANAGEMENT AND DEVELOPMENT

DEPARTMENT OF COMMUNITY HEALTH

BSC HEALTH SYSTEMS MANAGEMENT AND DEVELOPMENT AND COMMUNITY HEALTH PRACTICE

END OF FIRST SEMESTER EXAMINATION SEPTEMBER -DECEMBER 2023

HMD 224/CHP325 PROJECT MANAGEMENT IN HEALTH

TIME:		Two Hours

Date	:                       5th December 2023

TIME	:		Two (2) Hours      Start-----9.00------------------End………11.00…………

INSTRUCTIONS TO CANDIDATES

- This exam is out of 70 marks

- Section-A is compulsory with a Total of 30 Marks

- Answer any TWO (2) questions in Section B

Read carefully the additional instructions preceding each section.

SECTION A

SHORT ANSWER QUESTIONS – TOTAL of 30 MARKS

Question 1

- Define the following concepts as used in health project management:

  - Community mapping							(2 marks)

  - Participatory monitoring							(2 marks)

  - Outcome indicator							(2 marks)

  - Agile methodology 							(2 marks)

- Highlight the following knowledge areas in project management

      - Project scope management 						(3 marks)

      - Project integration management 						(3 marks)

      - Project risk management 						            (3 marks)

      - Project cost management 							(3 marks)

- State any two benefits of carrying out the stakeholder analysis in project design. (2 marks)

- Differentiate between community capacity assessment and needs assessment in health project management. 					           				(4 marks)

- Outline the hierarchy of objectives in a logical framework matrix.		(4 marks)

SECTION B

LONG ANSWER QUESTIONS: ANSWER ANY TWO (2) QUESTIONS

EACH QUESTION HAS 20 MARKS

Question 2

A problem of high prevalence of sexually transmitted infections among the youth has been identified in an informal settlement in a developing country in Africa.

- Sketch the problem tree to analyze the issue at hand.				(8 marks)

- Propose a project that can be implemented to address this problem. 		(4 marks)

- Write down two SMART objectives in line with the problem tree that you have sketched and the project that you have selected above. 						(4 marks)

- Identify any four groups of key stakeholders for this project and explain how you can involve them in the project. 								(4 marks)

Question 3

Discuss five main precautions that should be taken when writing an unsolicited concept paper in a grant application. 								(20 marks)

Question 4

Formulate four different types of objectively verifiable indicators that will be used in monitoring and evaluation of a project designed and implemented to address the issue of substance abuse among young people in Nairobi, Kenya. 						(20 marks)