102106T4COH

# COMMUNITY HEALTH LEVEL 6

# HE/OS/CH/CC/01/6/A

MONITOR AND EVALUATE COMMUNITY HEALTH PROGRAMMES

Nov. /Dec. 2022

THE KENYA NATIONAL EXAMINATIONS COUNCIL

WRITTEN ASSESSMENT

Time: 3 hours

## INSTRUCTIONS TO CANDIDATES

This paper consists of TWO sections: A and B.

Maximum marks for each question are indicated in brackets ().

Answer questions as per instructions in each section.

You are provided with a separate answer booklet.

This paper consists of THREE (3) printed pages.

Candidates should check the question paper to ascertain that all the pages are printed as indicated and that no questions are missing.

SECTION A  (40 MARKS)

Attempt ALL the questions in this section

- Highlight three importance of monitoring projects in the community.		        (3 marks)

- Give three reasons why we disseminate data to the community.		        	        (3 marks)

- Outline three main steps in project cycle management.		                  	        (3 marks)

- Distinguish between Monitoring and Evaluation in terms of their purpose and area of focus.											           	        (4 marks)

- Highlight three importance of an evaluation plan during the process of project evaluation.                     	                                                                                                                                (3 marks)

- Outline five types of monitoring in a project management.			        (5 marks)

- Explain two indicators used in monitoring and evaluation.  			        (2 marks)

- Differentiate between project inputs and project outputs.			        (2 marks)

- Indicate three methods used in carrying out project monitoring. 		        (3 marks)

- Give three reasons why an organization should incorporate plans for monitoring

and evaluation during the early stages of program development.		        (3 marks)

- Outline five uses of monitoring and evaluation findings.	                                (5 marks)

- Mention four common tools used by community health workers to collect and gather information during the process monitoring and evaluation. 	                                (4 marks)

SECTION B  (60 MARKS)

ANSWER ANY THREE (3) QUESTIONS IN THIS SECTION

- As a community health officer based in Kibera slum you have been tasked to monitor and evaluate projects that are funded by the Non-Governmental organizations in that area.

- Discuss four steps followed in selection of SMART indicators.		      (10 marks)

- Explain any two resources used in monitoring and evaluation.		      (10 marks)

- Discuss any five principles of a good monitoring and evaluation system.	      (20 marks)

- Patrick is one of the employees in Mazuri children’s home having conducted a field survey on hand hygiene in that community unit, he is required to analyse the data to finalize the report. Discuss the four phases of data analysis he will use to analyse the information.

(20 marks)

- An evaluation plan (proposal) is a written document that guides us on how to conduct the evaluation process.

- Explain the six steps considered when formulating an effective evaluation plan.												      (18 marks)

- Identify two challenges one is likely to encounter during the evaluation process.												       (2 marks)

THIS IS THE LAST PRINTED PAGE.